## Sheet2
CRNumber | Milestone | Activity | Task | PlanStartDate | PlanEndDate | Users
CRM-LEADMGT-4 | User Interface | User Interface Design | Design a single page application with BAPL product list | 31-Aug-2023 | 31-Aug-2023 | tonmoy.rudra@bsrm.com
CRM-LEADMGT-4 | User Interface | User Interface Design | Create a Buy Now Button and after click its redirect to Google From | 31-Aug-2023 | 01-Sep-2023 | tonmoy.rudra@bsrm.com
CRM-LEADMGT-4 | User Interface | Mobile responsive | Mobile Responsive User interface | 01-Sep-2023 | 05-Sep-2023 | tonmoy.rudra@bsrm.com
CRM-LEADMGT-4 | Build Server | Upload Server | Upload on server and get the Live URL | 01-Sep-2023 | 05-Sep-2023 | tonmoy.rudra@bsrm.com
CRM-LEADMGT-4 | QR Code Generate | QR Code Generate | Generate a QR code with this Live URL. | 01-Sep-2023 | 05-Sep-2023 | tonmoy.rudra@bsrm.com
CRM-LEADMGT-4 | UAT | UAT | UAT by internal Team | 05-Sep-2023 | 06-Sep-2023 | tonmoy.rudra@bsrm.com
CRM-LEADMGT-4 | UAT | UAT | UAT BY User | 06-Sep-2023 | 06-Sep-2023 | tonmoy.rudra@bsrm.com